## Person 2 RTM
CivicConnect M2 Person 2 traceability
Source: CivicConnect M1 Person 2 draft, 9 September 2026. Original wording preserved.
Implementation evidence is separate from team approval. Scroll right for code, tests and pending review links.
Requirement ID | Original requirement wording | Stakeholder or source | Priority | Original acceptance criteria | Quality driver and architecture handoff | Data and persistence impact | Interface or design handoff | Technology decision | Implementation evidence | Verification evidence | Implementation status | ADR risk or change | Approval status | GitHub evidence | M3 test cases | M3 expected result | M3 actual evidence | M3 defects and acceptance status | M4 acceptance assessment | M4 acceptance score | M4 evidence and remaining gaps | M4 assessed candidate | M4 review status
FR-001 | Sign In and Out The platform shall authenticate users and apply their assigned role permissions (Requester, Staff, Oversight). Users must be able to securely sign out. | All users; MB §§3, 16 | Must | AC-F01: A valid login grants access only to authorised features. Invalid credentials prevent login. Post sign-out, browser navigation backward cannot retrieve or modify protected records. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | users, sessions; hashed credentials and expiry | POST /api/login; GET /api/me; POST /api/logout | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | src/infrastructure/auth.js; src/http/app.js | T22, T23 | Implemented backend; client integration pending | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T23, M3-S01 | 200 login;403 badCSRF/origin;201 submit;404 isolation;401 logged-out read; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | Login, access checks and logout tested; automated protected access after logout. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-002 | Submit Request The system shall accept requests containing a title, description, and active category (location or asset details remain optional). Upon submission, it auto-assigns a unique reference ID, creation time, Normal priority, and Received status. | Requester; MB §3 | Must | AC-F02: Submitting a valid form creates a retrievable database record and displays a confirmation screen. Missing required fields blocks submission, highlights the missing inputs, and retains already entered text. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | requests required fields/defaults/reference; receipt activity | POST /api/requests | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.create; RequestRepository.insert/activity; migration 001 | T01, T02, T21, T23 | Implemented backend; UI confirmation pending | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T01, T02, T21, T23, M3-U01, M3-U02, M3-S01, M3-S02 | Default Received/Normal, unique reference and one receipt; 400; no request records; Text preserved; table intact; 200 login;403 badCSRF/origin;201 submit;404 isolation;401 logged-out read; 0 and 121 rejected;1 and120 accepted; Maximum accepted;above maximum rejected;optional blank accepted; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read; 400 invalid;404 isolated reads;reason required;Rejected public reason;409 stale without extra activity | Automated cases pass. Browser submission and required-input retention passed. Full CC references in requester/staff queues and staff details passed retests on 14 October. See browser-acceptance.md; correction commit 16e5594. | DEF-M3-004 fixed and browser retested; correction included in main. Full requirement acceptance remains separate. | Met | 1 | Creation/defaults/retrieval tests; browser confirmation in earlier checks; M4 submission and blank-title retention passed. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-003 | Controlled Categories The system shall restrict category selection to an approved active list. Existing requests must maintain their category label if that category is later retired. | Requester / Staff; MB §3 | Must | AC-F03: Active categories are accepted. Invalid or inactive category submissions are rejected. Deactivating or retiring a category does not remove or alter category labels on existing ticket histories. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | categories.active; requests.category_label snapshot | GET /api/categories; POST /api/requests | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.create; category query; migration 001 | T02, T03 | Implemented backend; catalogue admin UI not included | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T02, T03 | 400; no request records; Historical label preserved; new submission rejected | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | T02/T03 verify active categories, rejection and preserved historical labels. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-004 | Submission History The system shall allow requesters to view a list of their past submissions and inspect current status, submitted details, and visible history (including closed and rejected tickets). | Requester; MB §3 | Must | AC-F04: Requesters can see all their submitted records and associated status details upon refreshing. Requesters cannot view or access another user's submissions. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | requester_id scoped query and public activities | GET /api/requests; GET /api/requests/{id} | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestRepository.scoped/history; RequestService.authorized/detail | T04, T09, T23 | Implemented backend; UI integration pending | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T04, M3-S02 | Empty list and 404 detail; 400 invalid;404 isolated reads;reason required;Rejected public reason;409 stale without extra activity | Automated isolation cases pass. Browser requester2 queue isolation, final Closed status visibility and full reference display passed. See browser-acceptance.md. | DEF-M3-004 fixed and retested; DEF-M3-006 requester details/history remains open. | Met | 1 | Requester list/status and ownership isolation covered by existing tests. PR #29 adds details and public history; 17 October screenshots confirm submitted fields, receipt/assignment history and resolution feedback. Refresh/back passed. Separate final-candidate release verification remains pending. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-005 | In-App Feedback The system shall retain in-platform activity updates for receipt, assignment, rejection, priority updates, due-date changes, status transitions, and public comments. Resolution and closure must be clearly highlighted. | Requester; MB §3 | Must | AC-F05: After any update, the requester’s dashboard displays the timestamp, reference ID, and clear explanation note. Rejections display reasons, and resolutions display summaries. Internal staff notes remain hidden. Feedback persists across sign-outs. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | public activities saved with each workflow operation | GET /api/requests/{id} | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestRepository.activity/history; RequestService.mutate | T01, T09, T19, T20 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T09, M3-S01 | Requester cannot see internal note or snapshots; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read | after-fix.tap: named tests pass; browser/operational checks not inferred | Backend activity tests pass; DEF-M3-006 complete requester feedback/history UI remains open. | Met | 1 | 18 October: public notes, scheduling updates, resolution/closure feedback and requester sign-out persistence confirmed. Internal notes hidden. Existing automated activity/privacy cases pass. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-006 | Authorised Work Queue The system shall display tickets within a staff member's authorised categories and allow full inspection of submitted details, owner, priority, due time, status, and history. | Staff; MB §3 | Must | AC-F06: Queues display only in-scope category tickets for the logged-in staff member. Opening an in-scope record displays all fields. Direct access attempts to out-of-scope categories are denied. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | staff_categories eligibility; complete request records | GET /api/requests; GET /api/requests/{id} | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestRepository.eligible/scoped; RequestService.authorized | T05 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T05, M3-S02 | Read and mutation denied; 400 invalid;404 isolated reads;reason required;Rejected public reason;409 stale without extra activity | Automated scope tests pass. Browser IT staff queue isolation and Facilities staff access passed. Full staff queue/details references passed retests on 14 October. | DEF-M3-004 fixed and retested; DEF-M3-006 complete staff fields/history remains open. | Met | 1 | 18 October: staff queue/details show submitted fields, owner, priority, due date and history. Existing backend category/direct-access tests pass. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-007 | Search, Filter, and Sort The system shall support reference code or title searches, filters (by status, category, owner, priority, creation date), and ascending/descending sorting by creation date or due date. | Staff; MB §3 | Must | AC-F07: Search and combined filters return exact matching records within authorised categories. Sorting correctly orders results, placing unscheduled/undated items last. Empty searches show a clear 'No results found' message. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | scope before filtering; UTC date range; due nulls last | GET /api/requests?q=&status=&category=&owner=&priority=&from=&to=&sort=&direction= | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.list/dateRange | T14, T16 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R02 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T14, T16 | Only matches; null due last; unknown query empty; 400 | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | 18 October: combined title/status filtering, no-results message and reset passed in the browser. Search/filter/sort controls implemented; existing automated combined-filter/null-last-sort cases pass. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-008 | Assign Responsibility Authorised staff shall accept/assign a Received request (updating status to Assigned) or reassign an active request to another eligible team member. Assignment requires setting a priority and due time. | Staff; MB §3 | Must | AC-F08: Assignment locks the ticket to one category-authorized owner. Ineligible owners or missing due dates abort the assignment. Reassignment preserves the prior owner in the history log and notifies the requester. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | owner_id, priority, due_at, status, version; eligibility; activity snapshots | POST /api/requests/{id}/assign | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.mutate; RequestRepository.update/activity/transaction | T06, T10, T11, T20 | Implemented; measured M4 checks passed in the recorded local environment; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06; CR-P2-001 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T06, T20, M3-S01 | Invalid assignment rejected; valid assignment version 2; New owner saved; old owner retained in audit; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read | Automated assignment/reassignment cases pass. Manual browser assignment passed. See after-fix.tap and browser-acceptance.md. | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | Assignment and reassignment controls implemented. Isolated automated check changed eligible owner 3 to 5, verified prior/new audit values and requester-visible feedback, and rejected ineligible/missing-date assignments without mutation. Browser controls were inspected; this reassignment execution was API-based. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-009 | Priority and Due Date Management Authorised staff shall set or update priorities (Low, Normal, High) and set target completion dates (must be later than creation time). | Staff / Oversight; MB §§2, 3 | Must | AC-F09: Valid priorities and future due dates are saved successfully. Past due dates or invalid values are rejected. Modifications retain previous values, actor ID, timestamp, and update reason in the audit history. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | priority/due_at update with before/after actor and reason | POST /api/requests/{id}/schedule | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.mutate; policy.futureDate; activities | T19 | Implemented; scheduling browser check and automated validation/audit evidence recorded. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06; CR-P2-001 | CR-P2-001 approved by Edward, Albert and Amelia on 18 October 2026; see PR #28 discussion. Final release approval remains separate. | https://github.com/Amelia-VanDerWalt/CivicConnect/pull/28 | T19, M3-U03, M3-U06 | Before/after values, actor, timestamp and reason recorded; only Low, Normal and High accepted; only future timezone-bearing due dates accepted. Historical M3 expectation: CR-P2-001 was pending at that time. Current decision: approved by the team on 18 October 2026; see PR #28. | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | AC-F09 supported by T19, M3-U03 and M3-U06, plus the recorded 18 October browser scheduling check. Valid priorities/future dates save; invalid values are rejected; audit retains previous values, actor, timestamp and reason. CR-P2-001 approved in PR #28: due dates must be strictly later than server current time when assigned or rescheduled. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-010 | Controlled Lifecycle Transitions Staff shall transition request statuses strictly following Rule R2. Rejections require reason notes, resolutions require summaries, and closure requires prior resolution. | Staff; MB §3 | Must | AC-F10: Valid state transitions execute properly with mandatory notes. Missing notes or invalid state jump attempts are blocked without changing database state. Resolution and closure trigger requester notifications. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | status enum; transition map; resolved_at; required notes | POST /api/requests/{id}/status | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | policy.transition; RequestService.mutate | T07, T08 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T07, T08, M3-U05, M3-S01, M3-S02 | Valid order succeeds; invalid transitions rejected; Reason required; rejected record terminal; Only valid transitions with required reason accepted; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read; 400 invalid;404 isolated reads;reason required;Rejected public reason;409 stale without extra activity | Automated lifecycle cases pass. Browser invalid Received-to-Closed jump blocked. On 14 October, blank resolution/rejection notes were blocked without status changes; supplied summaries/reasons allowed transitions. Correction commit 16e5594. | DEF-M3-005 fixed and browser retested; correction included in main. Complete requester notification acceptance remains separate. | Met | 1 | 18 October: Assigned to In progress to Resolved to Closed executed. Empty resolution summary blocked. Requester sees final status, summary and highlighted history. Existing rejection/transition tests pass; withdrawn 17 October assumptions remain withdrawn. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-011 | Work History & Action Logging Authorised staff shall append work logs, progress notes, and resolution text. Every note must be explicitly flagged as Requester-Visible or Internal-Only before saving. | Staff; MB §3 | Must | AC-F11: Saved notes preserve author, timestamp, text, and visibility flag. Requesters only see public notes. Corrections are appended as new notes; historical logs cannot be edited or deleted through normal user interfaces. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | append-only activities; explicit Public/Internal visibility | POST /api/requests/{id}/note | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.mutate; RequestRepository.history; activity triggers | T09, T12, T24 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05; P2-R08 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T09, T24, M3-S01 | Requester cannot see internal note or snapshots; 400; no extra history; 201 create;200 valid changes;Closed visible;internal note hidden;logout denies read | after-fix.tap: named tests pass; browser/operational checks not inferred | Automated visibility and append-only cases pass; DEF-M3-006 complete work-history UI remains open. | Met | 1 | 18 October: explicit Public/Internal browser note controls saved notes; public note visible to requester and Internal note hidden. Staff history displays metadata/visibility. Existing immutable-history cases pass. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-012 | Management Reporting The system shall generate aggregate reports showing open, overdue, resolved, closed, and rejected counts by category for defined date ranges. It shall report undated tickets, ownership, and MTTR as defined in R4. | Oversight; MB §3 | Must | AC-F12: Generated report metrics, boundary date filters, and breakdown counts match underlying data exactly. Only resolved/closed tickets calculate into MTTR. Oversight roles cannot modify tickets without staff rights. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | category counts, open/overdue/undated, owner counts, first-resolution MTTR | GET /api/reports?from=&to= | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestService.report/dateRange | T13, T15, T16 | Implemented; selected automated and 18 October browser checks passed; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R02; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T13, T15, T16 | Oversight reads but cannot write; requester denied reports; Total 3/open 2/overdue 1/undated 1/resolved 1/MTTR 2h; 400 | after-fix.tap: named tests pass; browser/operational checks not inferred | Automated report calculations pass; DEF-M3-006 reporting UI remains open. | Met | 1 | 18 October: Oversight report screen, date filtering, empty results and read-only details passed. Existing automated report/date/MTTR/role cases pass; browser observations do not independently recompute every metric. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
FR-013 | Audit Trail The system shall maintain an immutable, chronological log of creation, ownership updates, priority shifts, due-date adjustments, status changes, and work logs. | Staff / Oversight; MB §§2, 3 | Must | AC-F13: System updates generate sequential audit log records capturing actor ID, timestamp, prior values, and new values. Standard interfaces prevent editing or deleting audit logs. Requesters cannot view internal audit details. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | chronological activities with actor, time, old/new snapshots; triggers | Read in GET /api/requests/{id}; no audit update/delete API | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | RequestRepository.activity/history; migration 001 | T11, T12, T19, T20 | Append-only normal operations; not administrator-proof | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R08 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T11, T12, T19, T20 | Request status/version rolls back; Database rejects both; Before/after actor and reason recorded; New owner saved; old owner retained in audit | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | Audit metadata, prior/new values, immutability and requester restrictions covered by existing tests. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-001 | Access Control & Least Privilege The platform shall enforce strict role-based access checks on all protected API endpoints and system actions, blocking unauthorised direct backend requests. | All users; MB §16 | Must | AC-N01: Role matrix tests verify that unauthorised read/write attempts (e.g., cross-requester views, out-of-scope staff edits) fail cleanly without exposing sensitive system information or altering state. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | users.role, requester_id and staff_categories authorization | All protected routes | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | Auth.session; RequestService.authorized; scoped queries | T04, T05, T13, T22, T23 | Initial role/scope checks passed; wider assurance pending | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T04, T05, T13, T22, T23, M3-I01 | Empty list and 404 detail; Read and mutation denied; Oversight reads but cannot write; requester denied reports; 401 and no-store; 200 login;403 badCSRF/origin;201 submit;404 isolation;401 logged-out read; Dynamic port;assets200;health ok;configured-Origin login200 | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | Selected role-matrix tests cover unauthorised requester/staff/oversight operations. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-002 | Data & Secret Protection Transmitted credentials and data must be encrypted in transit (TLS). Operational secrets, API keys, and passwords must be excluded from code repositories, client-side files, and logs. | All users / Team; MB §§9, 16 | Must | AC-N02: Network traffic audits confirm HTTPS/TLS encryption. Automated repository and log scans confirm no hardcoded secrets or credentials exist in codebase or build outputs. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | password hash and session token hash; no production secrets included | HTTPS proposed; Secure cookie option; sanitized errors | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | auth.js; app.js; .env.example; .gitignore | CI run #30 reported successful on commit 98ff24f459de205cb125ab88a6c26e0ef5b27912: selected static/security checks, repository hygiene checks and npm audit passed. The Person 3 handoff reports 15 JavaScript files checked, no unignored .env/SQLite artefacts, no selected hard-coded secret-token patterns, and no high/critical npm dependency vulnerabilities. This is a selected pattern check, not a comprehensive secret/log scan; production TLS is not demonstrated. | Partial: selected static/security and repository-hygiene checks have CI evidence; production TLS, network traffic audit, and comprehensive repository/build/log secret scanning remain unverified. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R05; P2-R07 | Original supplied status: Draft; team approval pending | [PR #23 — CI, security, staging and performance implementation](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/23); [PR #25 — merged Person 3 handoff](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/25); [successful GitHub Actions run #30 on commit `98ff24f459de205cb125ab88a6c26e0ef5b27912`](https://github.com/Amelia-VanDerWalt/CivicConnect/actions/runs/38797557518); [PR #27 — PED/RTM integration and review](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/27). The cited CI run is evidence for its recorded commit, not a substitute for a fresh run on the final submitted SHA. | T21, M3-I01, M3-I02 | Text preserved; table intact; Dynamic port;assets200;health ok;configured-Origin login200; 404 traversal;405 unsupported method | Person 3 handoff reports selected security checks passed in CI: 15 JS files passed syntax/static checks; no exposed .env/SQLite runtime artefacts; no selected hard-coded secret-token patterns; no high/critical npm dependency vulnerabilities. The configured audit threshold is high severity. No claim of production TLS or exhaustive secret/log scanning. | Selected CI checks evidenced; TLS and comprehensive secret/log scan remain open. DEF-M3-002 is recorded as fixed in the defect register, but the original NFR acceptance criterion is only partially evidenced. | Partially Met | 0.5 | Selected repository hygiene checks exist; TLS and complete repository/log/build-output coverage are not established. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-003 | Data Integrity & Concurrency Acknowledged transactions must persist through system restarts. Failed operations must roll back completely. Concurrent edits must not cause data loss or duplicate records. | Requester / Staff; MB §§2, 4 | Must | AC-N03: Database recovery checks confirm zero state loss after forced application restarts. Failed updates leave no partial entries. Concurrent updates are handled cleanly without silent overwrites. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | atomic transactions, durable store, expected-version check | 409 on stale updates; 500 on unexpected failures | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | database.js; RequestRepository.transaction/update | T10, T11, T17; crash/multi-process tests Planned | Implemented; measured M4 checks passed in the recorded local environment; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R01; P2-R02 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | T10, T11, T17, M3-U04, M3-S02 | Second gets 409 without extra audit; Request status/version rolls back; Reference retained; integrity_check ok; Only positive safe integer accepted; 400 invalid;404 isolated reads;reason required;Rejected public reason;409 stale without extra activity | after-fix.tap: named tests pass; browser/operational checks not inferred | Selected automated behaviour verified; full acceptance/approval separate | Met | 1 | Forced application termination preserved all acknowledged requests, activities, accounts and category permissions. Integrity checks passed. Existing rollback/stale-edit cases and the additional conflict check passed. Process-crash evidence does not establish host power-loss behaviour. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-004 | System Responsiveness Under load (5,000 active records, 20 concurrent users), 95% of read operations (search, lists, details) complete within 2.0s, and write operations complete within 3.0s. | All users; MB §§4, 11 | Should | AC-N04: A 15-minute steady-state load test (80% reads, 20% writes) measures client-to-server transaction times, verifying performance target compliance. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | indexes; present lists/reports filter scoped rows in memory | List/read/write timing across endpoints | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | migration 001 indexes; RequestService.list/report; perf-check.js | Performance smoke test in CI run #30 used 200 seeded requests, 10 live writes and 50 authenticated sequential read/filter requests. Reported results: total 943.37 ms; reads 50/50, average 4.51 ms, p95 6.81 ms, max 13.08 ms; writes 10/10, average 5.05 ms, p95/max 9.99 ms. These are smoke-test figures only. | Implemented; measured M4 checks passed in the recorded local environment; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R02 | Original supplied status: Draft; team approval pending | [PR #23 — CI, security, staging and performance implementation](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/23); [PR #25 — merged Person 3 handoff](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/25); [successful GitHub Actions run #30 on commit `98ff24f459de205cb125ab88a6c26e0ef5b27912`](https://github.com/Amelia-VanDerWalt/CivicConnect/actions/runs/38797557518); [PR #27 — PED/RTM integration and review](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/27). The cited CI run is evidence for its recorded commit, not a substitute for a fresh run on the final submitted SHA. | Person 3 performance smoke test: 200 seeded records, 50 authenticated read/filter requests, 10 authenticated writes; automated perf-check.js; CI run #30. | For the smoke workload, read p95 <= 2,000 ms and write p95 <= 3,000 ms; separately, formal NFR-004 requires the 5,000-record / 20-user / 15-minute workload. | CI smoke results reported: total 943.37 ms; read average/p95/max 4.51/6.81/13.08 ms (50/50 success); write average/p95/max 5.05/9.99/9.99 ms (10/10 success). Smoke thresholds passed; full load criterion not tested. | Smoke-test evidence incorporated. Full NFR-004 acceptance remains pending; TD-M3-001 scalability concern remains relevant. | Met | 1 | Formal local workload passed: 900.015 seconds, 5000 initial active records, 20 concurrent virtual users, 7200 reads and 1800 writes. Read p95 395.5 ms; write p95 42.86 ms. Response content and acknowledged-write persistence checked. Loopback HTTP environment; not a production network claim. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-005 | User Accessibility & Usability At least 80% of first-time test users can successfully submit a ticket and look up its status within 3 minutes without assistance. | Requester; MB §§2.1, 4 | Should | AC-N05: Unassisted usability testing with representative user groups tracks task completion time and error rates to verify target usability metrics. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | validation messages and persistence support submission workflow | API validation supports Person 3 UI | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | Backend implemented; UI and user study owned with Person 3 | Planned: representative user completion/time study | Supporting backend only; usability unverified | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | No additional automated acceptance evidence | See original acceptance criterion | No qualifying local automation result | Operational/quality acceptance pending | Not Met | 0 | Representative-user unassisted timed study not established. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-006 | WCAG Accessibility Compliance Submission, lookup, and staff queue workflows shall support full keyboard navigation, display visible focus indicators, and support 200% text zooming without loss of functionality. | All users; MB §§2.1, 4; W3C (2024) | Should | AC-N06: Interface testing verifies keyboard navigation (WCAG 2.1.1), visible focus styling (WCAG 2.4.7), and responsive page rendering at 200% font scaling (WCAG 1.4.4). | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | No direct schema effect; forms/readability owned by Person 3 | Errors support accessible client feedback | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | API only; no UI included in this P2 package | Planned: keyboard, focus, 200 percent text resize | Person 3 dependency; not WCAG verified | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R06 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | No additional automated acceptance evidence | See original acceptance criterion | Selected keyboard, visible-focus and 200% browser-zoom checks passed on 12-13 October. Longer references introduced on 14 October have not been retested at 200%. See browser-acceptance.md. | Partial manual evidence; full accessibility and text-resize acceptance not established. | Partially Met | 0.5 | Earlier selected keyboard/200% browser zoom checks passed; final-candidate font-scaling and complete workflow coverage not established. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-007 | Operational Monitoring System administrators must be alerted to service outages or critical infrastructure failures within 60 seconds. Diagnostic logs must exclude credentials and sensitive request text. | Operations team; MB §17 | Must | AC-N07: Simulated service outages confirm monitoring system alerts trigger within 60 seconds. System logs confirm error correlation IDs and timestamps are captured without logging sensitive payload data. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | Database health query; sanitized failure metadata | GET /health | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | app.js health route and correlation logger | Planned: external outage alert within 60 seconds | Health endpoint only; alerting not implemented | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R01; P2-R07 | Original supplied status: Draft; team approval pending | Pending actual issue/commit/PR/review; not fabricated | M3-I03 | Completed404;health query200 | after-fix.tap: named tests pass; browser/operational checks not inferred | Operational/quality acceptance pending | Not Met | 0 | Timed outage alerts and required diagnostic-log properties not established. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.
NFR-008 | Backup and Disaster Recovery In a critical data-loss event, system recovery shall occur within 60 minutes (RTO), with no more than 24 hours of lost data (RPO). | Organisation / Ops; MB §17 | Must | AC-N08: Simulated database recovery tests verify full system restoration from backup files within 60 minutes, ensuring recovered data integrity. | Integrity/least privilege where applicable; Person 1 confirms ASR ID and module allocation. Person 3 confirms UI/design allocation. | consistent backup snapshot; restore integrity | Operator script, no public recovery endpoint | Node 24.x / SQLite candidate; tested Node 24.19.0, SQLite 3.53.3 | scripts/backup.js; node:sqlite backup | Simulated staging verification ran the real server on an isolated staging SQLite database, completed the critical Requester/Staff lifecycle, created a backup snapshot, checked SQLite integrity and confirmed retained request state in the backup. Timed full restore and off-site recovery are not demonstrated. | Implemented; measured M4 checks passed in the recorded local environment; peer review pending. | ADR-P2-001; ADR-P2-002; ADR-P2-003; P2-R01; P2-R03 | Original supplied status: Draft; team approval pending | [PR #23 — CI, security, staging and performance implementation](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/23); [PR #25 — merged Person 3 handoff](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/25); [successful GitHub Actions run #30 on commit `98ff24f459de205cb125ab88a6c26e0ef5b27912`](https://github.com/Amelia-VanDerWalt/CivicConnect/actions/runs/38797557518); [PR #27 — PED/RTM integration and review](https://github.com/Amelia-VanDerWalt/CivicConnect/pull/27). The cited CI run is evidence for its recorded commit, not a substitute for a fresh run on the final submitted SHA. | T18 plus Person 3 staging/backup verification in CI run #30; simulated staging lifecycle and backup snapshot checks. | Create and validate a backup snapshot and preserve request data; separately prove full restore within 60 minutes and <=24 hours data loss to satisfy formal AC-N08. | Person 3 handoff reports simulated staging success, backup snapshot creation, PRAGMA integrity_check success and confirmation that the completed request exists in the backup. No timed full-system restore or off-site recovery evidence. | Backup snapshot/integrity evidence incorporated. Formal RTO/RPO and disaster-recovery acceptance remain pending; do not claim full NFR-008 compliance. | Met | 1 | Local backup restoration drill passed in 1262.77 ms. Restored server health, account access, requests, activities, permissions and report counts verified; zero acknowledged business-record loss in this drill. Fresh same-host snapshot; ongoing backup schedule, off-site retention and disaster-site recovery remain unproven. | Integrated assessment baseline: 5d6069822d4c125ce642a5d119a28ca4555a2b32. Release owner reports hosted CI #88 SUCCESS on this candidate. Original local test provenance: 11dc19df95590aa9daf518e0f04441cf389ad0ed plus runtime files fingerprinted in m4-formal-load-results.json | Assessment reconciled through merged PR #34 on 18 October 2026. CR-P2-001 approved and DEF-M3-006 closed through team confirmations in PR #28. Remaining Partial/Not Met results are retained. Production release is not approved; submission SHA and matching CI must be confirmed after the final documentation merge.